## Basic view
WBS | Key | Summary | Assignee | Status | Priority | Issue Type | Description | Due date | Linked Issues | Start date
1 | APM-2 | 1. Alcance técnico del proceso definido | Unassigned | Done | Medium | Workstream |  | Feb 27, 2026 |  | Feb 11, 2026
1.1 | APM-30 | 1.1. Contextualización del proyecto | Unassigned | Done | Medium | Task |  | Feb 27, 2026 | Linked issue cannot start until this issue finishes. APM-26 | Feb 23, 2026
1.1.1 | APM-32 | 1.1.1. Visita técnica a planta embotelladora | Unassigned | Done | Medium | Sub-task |  | Feb 27, 2026 |  | Feb 23, 2026
1.2 | APM-26 | 1.2. Especificación de productos a analizar | Unassigned | Done | Medium | Task |  | Feb 19, 2026 | Cannot start until linked issue finishes. APM-30, Linked issue cannot start until this issue finishes. APM-41, Linked issue cannot start until this issue finishes. APM-49 | Feb 14, 2026
1.2.1 | APM-28 | 1.2.1. Selección de 3 productos diferenciados | Unassigned | Done | Medium | Sub-task |  | Feb 16, 2026 |  | Feb 14, 2026
1.2.2 | APM-35 | 1.2.2. Identificación de envases utilizados | Unassigned | Done | Medium | Sub-task |  | Feb 17, 2026 |  | Feb 16, 2026
1.2.3 | APM-40 | 1.2.3. Recetas y parámetros críticos documentados | Unassigned | Done | Medium | Sub-task |  | Feb 19, 2026 |  | Feb 18, 2026
1.3 | APM-41 | 1.3. Identificación de procesos | Unassigned | Done | Medium | Task |  | Feb 23, 2026 | Cannot start until linked issue finishes. APM-26 | Feb 20, 2026
1.4 | APM-49 | 1.4. Indicadores por producto establecidos | Unassigned | Done | Medium | Task |  | Feb 26, 2026 | Cannot start until linked issue finishes. APM-26 | Feb 24, 2026
2 | APM-3 | 2. Levantamiento de información y análisis del proceso (AS-IS) | Unassigned | Done | Medium | Workstream |  | Mar 10, 2026 |  | Feb 13, 2026
2.1 | APM-27 | 2.1. Levantamiento técnico del proceso | Unassigned | Done | Medium | Task |  | Feb 14, 2026 | Linked issue cannot start until this issue finishes. APM-29, Linked issue cannot start until this issue finishes. APM-31, Linked issue cannot start until this issue finishes. APM-33, Linked issue cannot start until this issue finishes. APM-34 | Feb 13, 2026
2.2 | APM-29 | 2.2. Diagramas de operaciones y análisis de los procesos | Unassigned | Done | Medium | Task |  | Feb 18, 2026 | Cannot start until linked issue finishes. APM-27 | Feb 16, 2026
2.3 | APM-31 | 2.3. Flujo de materiales e información definido | Unassigned | Done | Medium | Task |  | Feb 21, 2026 | Cannot start until linked issue finishes. APM-27 | Feb 19, 2026
2.4 | APM-33 | 2.4. Estaciones, equipos y recursos caracterizados | Unassigned | Done | Medium | Task |  | Feb 24, 2026 | Cannot start until linked issue finishes. APM-27, Linked issue cannot start until this issue finishes. APM-39 | Feb 23, 2026
2.5 | APM-34 | 2.5. Tiempos base de operación estimados | Unassigned | Done | Medium | Task |  | Feb 27, 2026 | Cannot start until linked issue finishes. APM-27, Linked issue cannot start until this issue finishes. APM-36 | Feb 25, 2026
2.6 | APM-36 | 2.6. Value Stream Map estado actual elaborado | Unassigned | Done | Medium | Task |  | Mar 2, 2026 | Linked issue cannot start until this issue finishes. APM-37, Cannot start until linked issue finishes. APM-34 | Feb 28, 2026
2.7 | APM-37 | 2.7. Desperdicios/Muda identificados | Unassigned | Done | Medium | Task |  | Mar 4, 2026 | Cannot start until linked issue finishes. APM-36, Linked issue cannot start until this issue finishes. APM-42 | Mar 3, 2026
2.8 | APM-38 | 2.8. Indicadores AS-IS calculados | Unassigned | Done | Medium | Task |  | Mar 6, 2026 |  | Mar 5, 2026
2.9 | APM-39 | 2.9. Fallas típicas y parámetros de mantenimiento identificados | Unassigned | Done | Medium | Task |  | Mar 9, 2026 | Cannot start until linked issue finishes. APM-33, Linked issue cannot start until this issue finishes. APM-51 | Mar 7, 2026
3 | APM-4 | 3. Diseño del proceso futuro y estrategia de automatización | Unassigned | In Progress | Medium | Workstream |  | Mar 18, 2026 |  | Mar 10, 2026
3.1 | APM-42 | 3.1. Propuestas de objetivos de mejora definidos | Unassigned | Done | Medium | Task |  | Mar 11, 2026 | Cannot start until linked issue finishes. APM-37, Linked issue cannot start until this issue finishes. APM-43 | Mar 10, 2026
3.2 | APM-43 | 3.2. Propuesta Lean/preautomatización formulada | Unassigned | Done | Medium | Task |  | Mar 13, 2026 | Cannot start until linked issue finishes. APM-42, Linked issue cannot start until this issue finishes. APM-45, Linked issue cannot start until this issue finishes. APM-48 | Mar 12, 2026
3.3 | APM-45 | 3.3. VSM estado futuro elaborado | Unassigned | In Progress | Medium | Task |  | Mar 14, 2026 | Cannot start until linked issue finishes. APM-43 | Mar 14, 2026
3.4 | APM-48 | 3.4. Estrategia multiproducto definida | Unassigned | Done | Medium | Task |  | Mar 14, 2026 | Cannot start until linked issue finishes. APM-43, Linked issue cannot start until this issue finishes. APM-50 | Mar 14, 2026
3.5 | APM-50 | 3.5. Estrategia de cambio de producto definida | Unassigned | Done | Medium | Task |  | Mar 16, 2026 | Cannot start until linked issue finishes. APM-48 | Mar 16, 2026
3.6 | APM-51 | 3.6. Estrategia de fallas y recuperación definida | Unassigned | In Progress | Medium | Task |  | Mar 17, 2026 | Linked issue cannot start until this issue finishes. APM-52, Cannot start until linked issue finishes. APM-39 | Mar 17, 2026
3.7 | APM-52 | 3.7. Estrategia de rechazo y reproceso definida | Unassigned | In Progress | Medium | Task |  | Mar 18, 2026 | Cannot start until linked issue finishes. APM-51, Linked issue cannot start until this issue finishes. APM-70, Linked issue cannot start until this issue finishes. APM-57, Linked issue cannot start until this issue finishes. APM-62 | Mar 18, 2026
4 | APM-5 | 4. Arquitectura de automatización e instrumentación | Unassigned | To Do | Medium | Workstream |  | Apr 7, 2026 |  | Mar 28, 2026
4.1 | APM-70 | 4.1. Arquitectura ISA-95 documentada | Unassigned | To Do | Medium | Task |  | Mar 30, 2026 | Cannot start until linked issue finishes. APM-52, Linked issue cannot start until this issue finishes. APM-71, Linked issue cannot start until this issue finishes. APM-74 | Mar 28, 2026
4.2 | APM-71 | 4.2. Arquitectura de comunicaciones definida | Unassigned | To Do | Medium | Task |  | Mar 30, 2026 | Cannot start until linked issue finishes. APM-70, Linked issue cannot start until this issue finishes. APM-72 | Mar 30, 2026
4.3 | APM-72 | 4.3. Topología de red industrial definida | Unassigned | To Do | Medium | Task |  | Mar 31, 2026 | Cannot start until linked issue finishes. APM-71, Linked issue cannot start until this issue finishes. APM-73 | Mar 31, 2026
4.4 | APM-73 | 4.4. Lista de I/O y tags consolidada | Unassigned | To Do | Medium | Task |  | Apr 4, 2026 | Cannot start until linked issue finishes. APM-72, Linked issue cannot start until this issue finishes. APM-75, Linked issue cannot start until this issue finishes. APM-86 | Apr 1, 2026
4.5 | APM-74 | 4.5. PFD/P&ID del sistema elaborados | Unassigned | To Do | Medium | Task |  | Apr 6, 2026 | Cannot start until linked issue finishes. APM-70 | Apr 1, 2026
4.6 | APM-75 | 4.6. Requisitos de historización, eventos y lotes definidos | Unassigned | To Do | Medium | Task |  | Apr 7, 2026 | Cannot start until linked issue finishes. APM-73, Linked issue cannot start until this issue finishes. APM-92 | Apr 6, 2026
5 | APM-6 | 5. Gestión y evaluación de producción automatizada | Unassigned | To Do | Medium | Workstream |  | Apr 9, 2026 |  | Mar 16, 2026
5.1 | APM-53 | 5.1. Modelo AS-IS diseñado | Unassigned | To Do | Medium | Task |  | Mar 19, 2026 | Linked issue cannot start until this issue finishes. APM-54 | Mar 16, 2026
5.2 | APM-54 | 5.2. Modelo AS-IS validado | Unassigned | To Do | Medium | Task |  | Mar 23, 2026 | Cannot start until linked issue finishes. APM-53, Linked issue cannot start until this issue finishes. APM-55 | Mar 20, 2026
5.3 | APM-55 | 5.3. Escenarios AS-IS simulados | Unassigned | To Do | Medium | Task |  | Mar 26, 2026 | Cannot start until linked issue finishes. APM-54, Linked issue cannot start until this issue finishes. APM-56 | Mar 24, 2026
5.4 | APM-56 | 5.4. Desempeño AS-IS cuantificado | Unassigned | To Do | Medium | Task |  | Mar 28, 2026 | Cannot start until linked issue finishes. APM-55, Linked issue cannot start until this issue finishes. APM-57 | Mar 27, 2026
5.5 | APM-57 | 5.5. Modelo TO-BE diseñado | Unassigned | To Do | Medium | Task |  | Apr 1, 2026 | Linked issue cannot start until this issue finishes. APM-58, Cannot start until linked issue finishes. APM-56, Cannot start until linked issue finishes. APM-52 | Mar 30, 2026
5.6 | APM-58 | 5.6. Modelo TO-BE validado | Unassigned | To Do | Medium | Task |  | Apr 3, 2026 | Cannot start until linked issue finishes. APM-57, Linked issue cannot start until this issue finishes. APM-61 | Apr 2, 2026
5.7 | APM-61 | 5.7. Modelo TO-BE simulado | Unassigned | To Do | Medium | Task |  | Apr 6, 2026 | Cannot start until linked issue finishes. APM-58, Linked issue cannot start until this issue finishes. APM-59 | Apr 4, 2026
5.8 | APM-59 | 5.8. OEE y KPIs por escenario calculados | Unassigned | To Do | Medium | Task |  | Apr 8, 2026 | Cannot start until linked issue finishes. APM-61, Linked issue cannot start until this issue finishes. APM-60, Linked issue cannot start until this issue finishes. APM-108 | Apr 7, 2026
5.9 | APM-60 | 5.9. Comparativo AS-IS vs TO-BE consolidado | Unassigned | To Do | Medium | Task |  | Apr 9, 2026 | Cannot start until linked issue finishes. APM-59 | Apr 9, 2026
6 | APM-7 | 6. Planeación y evaluación de proyectos | Unassigned | To Do | Medium | Workstream |  | Mar 23, 2026 |  | Mar 4, 2026
6.1 | APM-76 | 6.1. EDT y diccionario EDT aprobados | Unassigned | To Do | Medium | Task |  | Mar 5, 2026 | Linked issue cannot start until this issue finishes. APM-77 | Mar 4, 2026
6.2 | APM-77 | 6.2. Cronograma base del proyecto estructurado | Unassigned | To Do | Medium | Task |  | Mar 7, 2026 | Cannot start until linked issue finishes. APM-76, Linked issue cannot start until this issue finishes. APM-78 | Mar 6, 2026
6.3 | APM-78 | 6.3. Plan de recursos consolidado | Unassigned | To Do | Medium | Task |  | Mar 10, 2026 | Cannot start until linked issue finishes. APM-77, Linked issue cannot start until this issue finishes. APM-79 | Mar 9, 2026
6.4 | APM-79 | 6.4. Presupuesto CAPEX/OPEX consolidado | Unassigned | To Do | Medium | Task |  | Mar 12, 2026 | Cannot start until linked issue finishes. APM-78, Linked issue cannot start until this issue finishes. APM-80 | Mar 11, 2026
6.5 | APM-80 | 6.5. Evidencias de precios recopiladas | Unassigned | To Do | Medium | Task |  | Mar 14, 2026 | Cannot start until linked issue finishes. APM-79, Linked issue cannot start until this issue finishes. APM-81 | Mar 13, 2026
6.6 | APM-81 | 6.6. Flujo de caja documentado | Unassigned | To Do | Medium | Task |  | Mar 16, 2026 | Cannot start until linked issue finishes. APM-80, Linked issue cannot start until this issue finishes. APM-82 | Mar 14, 2026
6.7 | APM-82 | 6.7. Indicadores financieros calculados | Unassigned | To Do | Medium | Task |  | Mar 17, 2026 | Cannot start until linked issue finishes. APM-81, Linked issue cannot start until this issue finishes. APM-83 | Mar 16, 2026
6.8 | APM-83 | 6.8. Propuesta de valor formulada | Unassigned | To Do | Medium | Task |  | Mar 18, 2026 | Cannot start until linked issue finishes. APM-82, Linked issue cannot start until this issue finishes. APM-84 | Mar 18, 2026
6.9 | APM-84 | 6.9.Oferta comercial estructurada | Unassigned | To Do | Medium | Task |  | Mar 20, 2026 | Cannot start until linked issue finishes. APM-83, Linked issue cannot start until this issue finishes. APM-85 | Mar 19, 2026
6.10 | APM-85 | 6.10. Modelo de negocio resumido definido | Unassigned | To Do | Medium | Task |  | Mar 23, 2026 | Cannot start until linked issue finishes. APM-84 | Mar 20, 2026
7 | APM-8 | 7. Celda de manufactura robotizada (diseño + RobotStudio + seguridad) | Unassigned | To Do | Medium | Workstream |  | Apr 11, 2026 |  | Mar 23, 2026
8 | APM-9 | 8. Controladores industriales (Grafcet + Ladder + Logix Emulate) | Unassigned | To Do | Medium | Workstream |  | Apr 18, 2026 |  | Apr 8, 2026
9 | APM-10 | 9. Gemelo digital integrado validado | Unassigned | To Do | Medium | Workstream |  | Apr 29, 2026 |  | Apr 20, 2026
9.1 | APM-100 | 9.1. Modelo 3D del sistema desarrollado | Unassigned | To Do | Medium | Task |  | Apr 21, 2026 | Linked issue cannot start until this issue finishes. APM-101 | Apr 20, 2026
9.2 | APM-101 | 9.2. Sensores y actuadores virtuales integrados | Unassigned | To Do | Medium | Task |  | Apr 23, 2026 | Cannot start until linked issue finishes. APM-100, Linked issue cannot start until this issue finishes. APM-102 | Apr 22, 2026
9.3 | APM-102 | 9.3. Integración con Logix Emulate implementada | Unassigned | To Do | Medium | Task |  | Apr 25, 2026 | Cannot start until linked issue finishes. APM-101, Linked issue cannot start until this issue finishes. APM-103 | Apr 24, 2026
9.4 | APM-103 | 9.4. Pruebas integradas ejecutadas | Unassigned | To Do | Medium | Task |  | Apr 27, 2026 | Cannot start until linked issue finishes. APM-102, Linked issue cannot start until this issue finishes. APM-104 | Apr 27, 2026
9.5 | APM-104 | 9.5. Validación funcional del sistema completada | Unassigned | To Do | Medium | Task |  | Apr 29, 2026 | Cannot start until linked issue finishes. APM-103 | Apr 28, 2026
10 | APM-11 | 10. SCADA/HMI (Ignition + ISA-101 + OPC) | Unassigned | To Do | Medium | Workstream |  | May 9, 2026 |  | Apr 20, 2026
10.1 | APM-92 | 10.1. Estándar HMI ISA-101 definido | Unassigned | To Do | Medium | Task |  | Apr 21, 2026 | Cannot start until linked issue finishes. APM-75, Linked issue cannot start until this issue finishes. APM-93 | Apr 20, 2026
10.2 | APM-93 | 10.2. Pantallas HMI diseñadas | Unassigned | To Do | Medium | Task |  | Apr 23, 2026 | Cannot start until linked issue finishes. APM-92, Linked issue cannot start until this issue finishes. APM-94 | Apr 22, 2026
10.3 | APM-94 | 10.3. Modelo de tags SCADA estructurado | Unassigned | To Do | Medium | Task |  | Apr 25, 2026 | Cannot start until linked issue finishes. APM-93, Linked issue cannot start until this issue finishes. APM-95 | Apr 24, 2026
10.4 | APM-95 | 10.4. SCADA en Ignition implementado | Unassigned | To Do | Medium | Task |  | Apr 29, 2026 | Cannot start until linked issue finishes. APM-94, Linked issue cannot start until this issue finishes. APM-96 | Apr 25, 2026
10.5 | APM-96 | 10.5. Comunicación OPC operativa | Unassigned | To Do | Medium | Task |  | May 2, 2026 | Cannot start until linked issue finishes. APM-95, Linked issue cannot start until this issue finishes. APM-97, Linked issue cannot start until this issue finishes. APM-99 | Apr 30, 2026
10.6 | APM-97 | 10.6. Alarmas, eventos e historización configurados | Unassigned | To Do | Medium | Task |  | May 5, 2026 | Cannot start until linked issue finishes. APM-96, Linked issue cannot start until this issue finishes. APM-98 | May 4, 2026
10.7 | APM-98 | 10.7. Interacción del operador habilitada | Unassigned | To Do | Medium | Task |  | May 6, 2026 | Cannot start until linked issue finishes. APM-97 | May 6, 2026
10.8 | APM-99 | 10.8. Validación funcional con gemelo digital completada | Unassigned | To Do | Medium | Task |  | May 9, 2026 | Cannot start until linked issue finishes. APM-96, Linked issue cannot start until this issue finishes. APM-109, Linked issue cannot start until this issue finishes. APM-108 | May 4, 2026
11 | APM-12 | 11. Validación y entregables finales del proyecto | Unassigned | To Do | Medium | Workstream |  | May 23, 2026 |  | May 11, 2026
11.1 | APM-108 | 11.1 Criterios de aceptación definidos | Unassigned | To Do | Medium | Task |  | May 11, 2026 | Cannot start until linked issue finishes. APM-59, Linked issue cannot start until this issue finishes. APM-110, Cannot start until linked issue finishes. APM-99 | May 11, 2026
11.2 | APM-109 | 11.2. Pruebas integrales end-to-end ejecutadas | Unassigned | To Do | Medium | Task |  | May 16, 2026 | Cannot start until linked issue finishes. APM-99 | May 11, 2026
11.3 | APM-110 | 11.3. Cuadro resumen final consolidado | Unassigned | To Do | Medium | Task |  | May 12, 2026 | Linked issue cannot start until this issue finishes. APM-111, Linked issue cannot start until this issue finishes. APM-112, Linked issue cannot start until this issue finishes. APM-113, Cannot start until linked issue finishes. APM-108 | May 11, 2026
11.4 | APM-111 | 11.4. Repositorio GitHub consolidado | Unassigned | To Do | Medium | Task |  | May 14, 2026 | Cannot start until linked issue finishes. APM-110 | May 13, 2026
11.5 | APM-112 | 11.5. Sitio web del proyecto completado | Unassigned | To Do | Medium | Task |  | May 16, 2026 | Cannot start until linked issue finishes. APM-110, Linked issue cannot start until this issue finishes. APM-113 | May 15, 2026
11.6 | APM-113 | 11.6. Video de proyecto producido | Unassigned | To Do | Medium | Task |  | May 19, 2026 | Cannot start until linked issue finishes. APM-110, Linked issue cannot start until this issue finishes. APM-115, Cannot start until linked issue finishes. APM-112 | May 13, 2026
11.7 | APM-115 | 11.8. Sustentación final preparada | Unassigned | To Do | Medium | Task |  | May 23, 2026 | Cannot start until linked issue finishes. APM-113, Linked issue cannot start until this issue finishes. APM-107 | May 20, 2026
11.8 | APM-116 | 11.9. Reflexiones de aprendizaje consolidadas | Unassigned | To Do | Medium | Task |  | May 23, 2026 |  | May 20, 2026
12 | APM-14 | 13. Entregables del curso | Unassigned | To Do | Medium | Workstream
12.1 | APM-19 | Taller 1 - Gestión de producción y automatización | Unassigned | Done | Medium | Entregable |  | Mar 6, 2026 |  | Mar 2, 2026
13 | APM-18 | Realización sitio web | Unassigned | To Do | Medium | Task |  | Mar 23, 2026 |  | Mar 20, 2026
14 | APM-17 | Realización repositorio | Unassigned | To Do | Medium | Task |  | Mar 23, 2026 |  | Mar 20, 2026
15 | APM-16 | Plan de reuniones y comunicaciones | Sergio Andres Bolaños Penagos | In Progress | Medium | Task |  | Mar 5, 2026 |  | Mar 2, 2026
16 | APM-15 | Conformación del equipo, roles, reglas | Sergio Andres Bolaños Penagos | Done | Medium | Task |  | Mar 5, 2026 |  | Mar 2, 2026
17 | APM-105 | 14. Fechas de sustentación | Unassigned | To Do | Medium | Workstream
17.1 | APM-106 | 14.1. Sustentación 1 | Unassigned | To Do | Medium | Task |  | Mar 27, 2026 |  | Mar 25, 2026
17.2 | APM-107 | 14.2. Sustentación 2 | Unassigned | To Do | Medium | Task |  | May 29, 2026 | Cannot start until linked issue finishes. APM-115 | May 25, 2026